## ProjectSchedule
ME781 Project_Insurance fraud detection
| IIT Bombay |  | Project Start: | 2021-10-01
| TrueInsurance Solutions |  | Today: | 2021-11-24
|  |  | Display Week: | 1 |  |  | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13
 | time axis 2021-09-27 to 2021-12-19
WBS Number | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2021-09-27 to 2021-12-19
1 | Problem definition
1.1 | • Customer (End-user) requirement |  | 100% | 2021-10-01 | 2021-10-15 | 15
1.2 | • Market survey for available solutions (Similar products and services available in the market) |  | 100% | 2021-10-11 | 2021-10-15 | 5
1.3 | • Key differentiator (how are you different from the available solutions) |  | 100% | 2021-10-11 | 2021-10-17 | 7
1.4 | • Your unique selling point (USP) |  | 100% | 2021-10-11 | 2021-10-17 | 7
1.5 | • How can you protect your USP |  | 100% | 2021-10-11 | 2021-10-17
1.6 | • Barrier to entry both by you and others |  | 100% | 2021-10-11 | 2021-10-17
1.7 | • Business case |  | 100% | 2021-10-11 | 2021-10-17
2 | Technology landscape assesment
2.1 | Patents |  | 100% | 2021-10-20 | 2021-11-03 | 15
2.2 | Published literature | All | 100% | 2021-10-20 | 2021-10-27 | 8
3 | Project planning
3.1 | Project Task breakdown |  | 100% | 2021-10-01 | 2021-10-15 | 15
3.2 | Project timeline (GANTT chart) |  | 100% | 2021-10-07 | 2021-11-01 | 26
3.3 | Roles and responsibilities (RASIC Chart) |  | 100% | 2021-10-07 | 2021-11-01 | 26
3.4 | Project monitoring | All | 100% | 2021-10-07 | 2021-11-20 | 45
4 | Conceptual design
4.1 | ML Model selection |  | 100% | 2021-10-15 | 2021-11-01 | 18
4.2 | ML Dataset selection |  | 100% | 2021-10-15 | 2021-11-01 | 18
4.3 | High Level activity object and class diagrams (using uml ) |  | 100% | 2021-10-28 | 2021-11-02 | 6
4.4 | Choice of language, operating system, data set, algorithms and dependencies on external libraries |  | 100% | 2021-10-15 | 2021-11-01 | 18
4.5 | High level sequence diagram with type of user i/p and o/p |  | 100% | 2021-10-28 | 2021-11-01 | 5
5 | Code development (phase 1)
5.1 | Coding convention best practices |  | 100% | 2021-10-25 | 2021-11-08 | 15
5.1.1 | Variable naming (Global constant, global variable, local variable, functions, classes, loop variables, etc.) |  | 100% | 2021-10-25 | 2021-11-08 | 15
5.1.2 | Coding style |  | 100% | 2021-10-25 | 2021-11-01 | 8
5.1.3 | Indentation style |  | 100% | 2021-10-25 | 2021-11-08
5.2 | Basic User interface |  | 100% | 2021-11-03 | 2021-11-22 | 20
5.3 | Output visualization |  | 100% | 2021-11-10 | 2021-11-15 | 6
6 | Code development (phase 2)
6.1 | Error handling (inbuilt python function) |  | 100% | 2021-11-01 | 2021-11-15
6.2 | Auto document generation ( Pydoc Pycco , |  | 100% | 2021-11-02 | 2021-11-15
6.3 | Code testing (using unittest or another library) |  | 100% | 2021-11-05 | 2021-11-15
7 | Product/service marketing
7.1 | Brochure development |  | 100% | 2021-10-30 | 2021-11-15
7.2 | Marketing presentation |  | 100% | 2021-10-25 | 2021-11-16
7.3 | 1 minute marketing video |  | 100% | 2021-11-25 | 2021-11-17
8 | Product demonstration
8.1 | Demonstration presentation |  | 100% | 2021-11-22 | 2021-11-23
8.2 | User manual |  | 100% | 2021-11-15 | 2021-11-20
Insert new rows ABOVE this one

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.