## Table 1
| WBS | Dushyant | Mudit | Vishvesh | Neha | Amit
Customer (End-user) requirement | 1.1
Market survey for available solutions (Similar products and services available in the market) | 1.2
Key differentiator (how are you different | 1.3
Your unique selling point (USP) | 1.4
How can you protect your USP | 1.5
Barrier to entry both by you and others | 1.6
Business case | 1.7
Patents | 2.1
Published literature | 2.2
Open libraries | 2.3
Proprietary libraries | 2.4
Project Task breakdown | 3.1
Project timeline (GANTT chart) | 3.2
Roles and responsibilities (RASIC Chart) | 3.3
Project monitoring | 3.4
ML Model selection | 4.1
ML Dataset selection | 4.2
High Level activity object and class | 4.3
Choice of language, operating system, data | 4.4 | I
High level sequence diagram with type of | 4.5
Variable naming (Global constant, global variable, local variable, functions, classes, loop variables, etc.) | 5.1.1
Coding style | 5.1.2
Indentation style | 5.1.3
Basic User interface | 5.2
Output visualization | 5.3
Error handling (inbuilt python function) | 6.1
Version control using GitHub | 6.3
Code testing (using unittest or another | 6.4
Brochure development | 7.1
Marketing presentation | 7.2
1 minute marketing video | 7.3
Demonstration presentation | 8.1
User manual | 8.2
The Rasic Chart is used to define the exact responsibilities of every party of a project. It is a part of the project package that is defined during the planning part. R: Responsible: the person responsible for this task A: Approve: the person giving the approval S: Supporting: the people giving support for the completion of the task I: Informed: the people to inform about the task C: Consulted: people who can act as expert in regard to the task Rule: Only one A and possible one R per Row WBS: The Work Breakdown Structure is in your Gantt chart or timing plan. For each line of it, there is a WBS.